## Slide 1
Unlocking Project Performance
Really collaborating to deliver enhanced performance on today’s major projects
Amsterdam - November 2022

## Slide 2: Projects leave serious money on the table – everyday!
Productivity at 50% through a $4bn GTL Plant Build
… above 10 inch
… 2 to 10 inch
Above ground fabrication CS Pipes
8m hours into project
CPI = 1.01
~1m hours over-performance
~1m hours under performance
15+% performance left behind
Projects are almost naturally set up to under-perform
Estimates
Contracts & Incentives
Ever changing activities
Immature teams
Accounting based reports
This is good news!
Because the opportunity to over-deliver is typically really big!

## Slide 3: With project values at $1m a day – performance counts!
$22bn Gas Project
$8bn Mine Project
Project Value $1.6b
Permitting 3 mths
Sourcing $45m
Engineering 3 mths
Construction 8 mths
Commissioning 6 mths
Bulk Earthworks 5 mths
Tailings Dam 3 mths
Concrete 2 mths
Structures 2 mths
M&E 4 mths
Systems 4 mths
Significant Savings Can Be Achieved

## Slide 4: We see collaboration as key to capturing this performance jump All project participants must shift from “safe plan for us” to “best result for all”
Project objectives are still met
Trade-offs being made are appropriate
While ensuring that:
Challenge assumed dependencies
Ask how internal steps to be converted to external steps
Eliminate non-productive time
Substitute processes to shorten duration
Implement more efficient operating procedures
Add resources
It’s sort of complicated out there…
Controls
Suppliers
Project Mgmt
Owner
Contractors
Authorities
Engineers
Site
Other Packages
HS&E
Contracts
…which gets in the way of performance
Schedule Estimates
Faster
Slower
Needs
Collaboration
Driven by
Disconnection
Collaboration must be grown
Right partners
Right team & mindset
Right incentives
Everyone can win
Trust that is built
Early engagement
Transparency
Stability
Notes: Collaboration: Change the contractual structure, working relationships and overall incentives within the project team and across the supply chain from focused on defending a “safe” “public” schedule to engaging early and constantly to drive down schedules and increase rates – to beat the schedule – every day

## Slide 5: We have found five areas that drive collaboration & performance
  Set-up the commercial environment to drive for better every day
Incentivise to Perform Together
2
  Significantly enhanced understanding and proactive management of the supply chain
Proactive Supply Chain Management
4
  Make the right decisions early enough
Strong Intelligent Owner Teams
1
Making Collaboration Work
  Real time information transparency across the project & its supply chain
One Digital Environment
5
  Performance comes from frontline – Release and enable them
Empower the Frontlines
3

## Slide 6: Strong Intelligent Owners Teams Make the right decisions early enough
1
Intelligent
Strong
Know what we specifically need
Understand the complete value trade offs
Recognise the value of time and timely decisions
Realise they ultimately hold all of the risk
Understand what will make each party successful
Fully informed on the status of work
&
Drive the best decisions for the project on time
Drive performance for the benefit of all
Remove risks early enough
Builds and protects a common performance culture

## Slide 7: Incentivise to perform together Set-up the commercial environment to drive for better every day
Part of the Team
Mutual Transparent
Want to Beat the Plan
Setup to Win Together
Progress
Performance
Improvement
Behaviours
Succeed not just Deliver
Aligned Incentives across Project Team
Common data environment
Common systems
Systems that help
Early & Committed
Bringing in Ideas
2
Right Regular Incentives
Business & Personal
Shared data, knowledge, needs and issues

## Slide 8: Empower the Frontlines Performance comes from frontline – Release and enable them
Frontline team leaders responsible and enabled to drive performance
Supply chain 100% focused on feeding construction on time and in full
Leadership’s role is to remove the barriers
Controls provide teams with targets, structure and insights to perform and improve
Execution driven performance
3
Notes: Empowerment: Ensure all critical team leads are focused on their key performance targets; and, the management team and supply chain are refocused on supporting the needs of these team leads

## Slide 9: Maximise Rate at every Frontline Continuously drive up rate through process discipline and improvement
Build process clarity; Ensure readiness; Remove variability; Simplify the process
5 weeks : 50% Improvement
Chart: 
| Wk 1 | 02/01 | 03/01 | 04/01 | 05/01 | 06/01 | 07/01 | Wk 2 | Wk 2 | Wk 2 | Wk 2 | Wk 2 | Wk 2 | Wk 3 | Wk 3 | Wk 3 | Wk 3 | Wk 3 | Wk 3 | Wk 3 | Wk 3 | Wk 4 | Wk 4 | Wk 4 | Wk 4 | Wk 4 | Wk 4 | Wk 4 | Wk 5 | Wk 5 | Wk 5 | Wk 5 | Wk 5 | Wk 5 | Wk 5
Actual | 6000 | 9000 | 12000 | 11900 | 8800 | 10950 | 13500 | 13550 | 9900 | 13500 | 15500 | 17000 | 19500 | 16000 | 13800 | 14800 | 13000 | 9000 | 9900 | 14500 | 14450 | 14300 | 13900 | 13900 | 14000 | 13000 | 13800 | 19000 | 11500 | 13000 | 14700 | 15500 | 15000 | 14800
Baseline, prior 12 months | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000
New Target | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000
Maximised Rate
Secure performance quickly
Be ready everyday
Be clear on target timings for each process step
Train and coach teams on good process
Reduce handover downtime
Improve the process
Continuously Improve
Improve the most valuable processes
Develop Efficient Processes with Clear Rates & Owners
Create a foundation for performance and improvement
Steps - Owners – Dependencies - Value
Engineering - Fabrication - Construction - Commissioning
For all key tasks
Is this a common mindset? Proactively supported by all?
Rail Construction – Line Laying
3
Notes: Rate: Embed a far tighter focus on maximising construction rate through a constant focus on process discipline and improvement

## Slide 10: Proactive Supply Chain Management Significantly enhanced understanding & proactive management of supply chains
4
Selection
More diligent
Set-up
Detailed specificity
Management
Digital transparency
Substantially more complex & longer; More constrained than understood
Increased use of offsite & modular; Less flex in the supply chain; Non-transferable risks
Understand the full cascaded supply chain of each supplier
Understand real criticality of packages, supply chain and suppliers
Adjust plan milestones & allowances to provide enough mitigation
Contract for precise digital transparency of progress
Do not assume risk is safely transferred
Be significantly more specific about due dates (within supply chain)
Digitally track up the supply chain cascade of specific items against readiness milestones
% complete is no longer good enough
Ensure prior or supporting teams (eg: engineering) remain on track
Use AI to ”see” the issues early

## Slide 11: Maintain 100% Readiness across the Supply Chain Shift the upstream focus to “Is everyone making construction ready on time?”
Does every supplier know specifically when they need to complete their task for each package?
Does the project know when a supplier misses a deliverable?
Act early enough to recover
Not an even bigger P6!
Give upstream teams the precision they need to be construction led
Stop using % complete to track performance – it’s “Done or Not Done”
Real demand bumps can be smoothed out
Recovery can be completed early enough
Following teams and construction can see packages will be ready
Package
Due & Status
Approvals
Design
Procure
Fabricate
Site Ready
Ship
“Engineering is usually too opaque. Readiness gives us the specificity engineering needs and the transparency the project needs. The same mindset flows down through the supply chain”
4
Notes: Readiness: Hold an absolute requirement for 100% readiness on all works every shift on all teams back-up the supply chain

## Slide 12: One Digital Environment Enabling All Real time information transparency across the project and its supply chain
Still too many text heavy reports that report past progress and protect the contract
Digital dashboards that highlight performance & progress from one source of truth
Digital twin that enables collaborative performance & supply chain efficiency
A. Set the Foundations
Digital twin
Common data structure
Common key software
Performance reporting
B. Secure the Value
Performance focus
Collaboration
Productivity apps
Blockchain payments
Plan - Share - Record - Automate - Track - See - Highlight - Assure
5
>>>>>
Notes: Transparency: Create “real-time” performance transparency across the project and its supply chain is critical to enabling the behaviours above and capturing the enhanced performance. The digital technology is now available to substantially change project performance transparency and rapidly highlight the most critical decisions so they are resolved before they become delays

## Slide 13
“It is the long history of humankind (and animal kind, too) that those who learned to collaborate and improvise most effectively have prevailed.” Charles Darwin
Questions?